## Dashboard
Music app - where we are
Everything here is calculated from the Roadmap sheet. Do not type in the grey cells.
Overall progress
Tasks done
Tasks in total
Complete
Waiting on you
Marked Next
Phase | Phase name | Done | Total | Progress | Status
0 | Foundation
1 | Release pipeline
2 | Schema + metadata
3 | ZIP upload (admin)
4 | Classification + review
5 | Discovery
6 | Player upgrades
7 | Offline downloads
8 | Offline mode
9 | In-app updater
10 | Admin deployment
11 | Quality + security
12 | Future ideas
Current phase (first one not finished):
Note: phases are numbered as in docs/PLAN.md (1-11), plus 0 = foundation and 12 = future ideas. Several phases run in parallel, so 'current phase' is just the earliest one with open tasks.

## Roadmap
Music app - roadmap and checklist
Click a cell in the Done column and pick ☑ (done) or ☐ (not done). Progress and the dashboard update by themselves.
Phase | Phase name | Task | Area | Done | When | Notes
0 | Foundation | Express + TypeScript API with JWT login (15 min access / 30 day refresh) | Backend | ☑ | Done
0 | Foundation | PostgreSQL on Aiven (users, songs, artists, albums, genres, playlists, likes, recently played) | Backend | ☑ | Done
0 | Foundation | Cloudflare R2 storage at media.deploymentportal.in | Backend | ☑ | Done
0 | Foundation | Backend deployed on Render free plan | Backend | ☑ | Done | Sleeps when idle; first request can take about a minute
0 | Foundation | Website on Cloudflare Pages (music.deploymentportal.in) | Web | ☑ | Done
0 | Foundation | Android app: player, playlists, likes, search, account page, logout | Mobile | ☑ | Done
0 | Foundation | Google sign-in on the website | Web | ☑ | Done
0 | Foundation | Google sign-in in the Android app | Mobile | ☐ | Later | Needs Android OAuth client + SHA-1 of the signing key (do after the private key)
0 | Foundation | Loading spinners, skip 5 s, app icon, direct APK download button on the website | All | ☑ | Done
1 | Release pipeline | GitHub Actions build on tag vX.Y.Z or manual run | CI | ☑ | Done
1 | Release pipeline | Version taken from the tag (versionName / versionCode) | CI | ☑ | Done
1 | Release pipeline | Emulator launch test with strict crash detection | CI | ☑ | Done
1 | Release pipeline | Publish music.apk + version.json to the 'latest' release; keep last good APK on failure | CI | ☑ | Done
1 | Release pipeline | Private release signing key stored in GitHub Secrets (replaces committed debug key) | CI | ☐ | Needs you | Decide before sharing the app widely - one reinstall needed (risk R1)
2 | Schema + metadata | Movie fields on albums; song soundtrack fields; draft/published status | Backend | ☑ | Done
2 | Schema + metadata | Labels (style / mood / genre), upload jobs and job items tables | Backend | ☑ | Done
2 | Schema + metadata | Telugu reference workbook import (49 artists, 36 draft movies, genres) | Backend | ☑ | Done | npm run import:reference - safe to repeat
3 | ZIP upload (admin) | Safe streaming ZIP upload (size, count, extension, path and magic-byte checks) | Backend | ☑ | Done
3 | ZIP upload (admin) | Movie-name detection from typed name or ZIP name; duplicate and vague-name checks | Backend | ☑ | Done
3 | ZIP upload (admin) | Rights confirmation required; songs created as drafts; per-file job progress | Backend | ☑ | Done
3 | ZIP upload (admin) | Admin upload screen with name confirmation flow | Admin | ☑ | Done
4 | Classification + review | Audio analysis (tempo, loudness, brightness, beat strength) with confidence scores | Backend | ☑ | Done | Rule-based heuristic-v1, not a trained model
4 | Classification + review | Admin review screen: approve / reject / edit / re-run, bulk approve | Admin | ☑ | Done
4 | Classification + review | Smart search using approved labels only (AND across labels and languages) | Backend | ☑ | Done
4 | Classification + review | Optional external classifier service (CLASSIFIER_URL) | Backend | ☑ | Done
4 | Classification + review | Train a real model on licensed, labelled audio (ml/train.py) | ML | ☐ | Optional | Needs a labelled dataset we do not have
5 | Discovery | Jamendo (Creative Commons) search and import to R2 | Backend | ☑ | Done
5 | Discovery | YouTube search, play-only in the official embedded player | All | ☑ | Done
5 | Discovery | Trending + popular Telugu videos on the website | Web | ☑ | Done
5 | Discovery | Trending + popular Telugu videos in the Android app | Mobile | ☑ | Done | Published in v0.2.2 / v0.2.3; not yet checked on a phone
5 | Discovery | Movie pages, label browser and combined search on the website | Web | ☑ | Done
5 | Discovery | Android: movie list and movie page screens | Mobile | ☐ | Next
5 | Discovery | Android: label browser (Melody + Romantic etc.) and new search | Mobile | ☐ | Next
5 | Discovery | Show workbook tags / example singers on movie pages | Web | ☐ | Later
5 | Discovery | Archive.org / Spotify embed as extra legal sources | Backend | ☐ | Optional
6 | Player upgrades | Repeat one / all and shuffle | Mobile | ☐ | Later
6 | Player upgrades | Queue screen (view, reorder, remove) | Mobile | ☐ | Later
6 | Player upgrades | Playback error recovery and retry | Mobile | ☐ | Later
6 | Player upgrades | Sleep timer | Mobile | ☐ | Optional
7 | Offline downloads | Choose and add a native file-download library | Mobile | ☐ | Later | Test on a real phone (risk R3)
7 | Offline downloads | Download button per song (only songs marked downloadable) | Mobile | ☐ | Later
7 | Offline downloads | Downloads list, storage use, delete download | Mobile | ☐ | Later
7 | Offline downloads | Play downloaded file without internet | Mobile | ☐ | Later
8 | Offline mode | Network status banner | Mobile | ☐ | Later
8 | Offline mode | Downloaded-only view when offline | Mobile | ☐ | Later
9 | In-app updater | Native module: read installed version, open system installer | Mobile | ☐ | Later | Android always shows its own confirmation (risk R4)
9 | In-app updater | Check version.json, show 'update available' (mandatory flag) | Mobile | ☐ | Later
9 | In-app updater | Download APK with progress, verify SHA-256, then install | Mobile | ☐ | Later
10 | Admin deployment | Admin panel built and working locally | Admin | ☑ | Done
10 | Admin deployment | Deploy admin site to Cloudflare Pages (root admin, NODE_VERSION=22, admin.deploymentportal.in) | Admin | ☐ | Needs you
10 | Admin deployment | Admin sign-in restricted to admin accounts; rotate the admin password | Admin | ☐ | Needs you
11 | Quality + security | Backend tests (49 passing) | Backend | ☑ | Done
11 | Quality + security | Docs: PLAN, MUSIC_ADMIN, CLASSIFICATION, PROJECT_OVERVIEW | Docs | ☑ | Done
11 | Quality + security | Run backend tests and type checks automatically on every push | CI | ☐ | Next
11 | Quality + security | Mobile and web tests | Mobile | ☐ | Later
11 | Quality + security | Rotate secrets that were shared in chat (Aiven, admin, Google, Jamendo keys) | Ops | ☐ | Needs you | Keep secrets only in Render / GitHub settings
11 | Quality + security | Keep-alive ping or paid plan so Render does not sleep | Ops | ☐ | Optional
11 | Quality + security | Error monitoring and uptime alerts | Ops | ☐ | Optional
12 | Future ideas | Separate App Locker app (fingerprint + PIN, Accessibility Service) | New app | ☐ | Optional | Decision pending; own folder and pipeline
12 | Future ideas | Lyrics, sharing playlists, follow artists | All | ☐ | Optional
12 | Future ideas | Admin analytics (plays, top songs) | Admin | ☐ | Optional
12 | Future ideas | iOS app | Mobile | ☐ | Optional | Needs a Mac and paid Apple account

## Architecture
Architecture - what talks to what
Component | Technology | Hosted on | Address / location | Talks to | Purpose | Cost
Android app | React Native 0.87 + TypeScript, Zustand, TanStack Query, react-native-track-player, WebView | Phone (APK from GitHub release) | mobile/ | Backend API, R2 (audio), YouTube player | Listening, playlists, likes, trending videos | Free
Website | React + Vite + TypeScript | Cloudflare Pages | music.deploymentportal.in (web/) | Backend API, R2, YouTube player, Google sign-in | Listening in a browser; Download-app button | Free
Admin panel | React + Vite + TypeScript | Your laptop now; Cloudflare Pages planned | admin/ | Backend API (/admin/...) | ZIP upload, review labels, publish, mark downloadable | Free
Backend API | Node + Express + TypeScript, zod, JWT, bcryptjs, multer, yauzl, music-metadata, bundled ffmpeg | Render (free plan) | musicapp-j5ji.onrender.com (backend/) | PostgreSQL, R2, Google, YouTube, Jamendo | All business logic, auth, search, uploads, classification | Free (sleeps when idle)
Database | PostgreSQL | Aiven (free plan, SSL) | backend/db/schema.sql | Backend only | Users, songs, movies, labels, playlists, upload jobs, classifications | Free
File storage | Cloudflare R2 (S3 API) | Cloudflare | media.deploymentportal.in | Backend writes; apps read audio and covers | Audio files, covers, posters | Free tier
Build pipeline | GitHub Actions | GitHub | .github/workflows/android.yml | GitHub release 'latest' | Build, sign, emulator test, publish APK + version.json | Free
Google sign-in | Google Identity / google-auth-library | Google | Google Cloud project | Website, backend | Sign in with Google | Free
YouTube Data API | REST | Google | Key stored on Render | Backend | Search and trending Telugu videos (played only in YouTube's own player) | Free quota
Jamendo API | REST | Jamendo | Key stored on Render | Backend | Creative Commons music search and import | Free
Classifier | Local rules over ffmpeg audio features (heuristic-v1); optional external service via CLASSIFIER_URL | Inside the backend | backend/src/classifier/ | Backend, R2 audio | Suggested labels with confidence for admin review | Free
Main flows
Listening | App / website -> Backend (list, search) -> PostgreSQL; audio streamed straight from R2
Admin upload | Admin panel -> Backend (stream ZIP) -> checks -> songs saved to R2 as DRAFT -> classify -> admin approves labels -> publish
Discovery | App / website -> Backend -> YouTube / Jamendo; Jamendo imports are copied to R2; YouTube only plays in the embedded player
Release | Tag vX.Y.Z -> GitHub Actions build + sign + emulator test -> release 'latest' (music.apk, version.json) -> website Download button
Download a song | App -> Backend (only if songs.downloadable) -> short-lived signed link -> R2

## API routes
Backend route map
Built = live now. Planned = needed by a later phase.
Group | Method | Path | Who | Purpose | Status
Health | GET | /health | Anyone | Server and integration status | Built
Auth | POST | /auth/register, /auth/login, /auth/refresh, /auth/google | Anyone | Create account, sign in, renew token, Google sign-in | Built
Songs | GET | /songs (sort, labels, language, q, limit, offset) | Anyone | List and filter published songs | Built
Songs | GET | /songs/search?q= | Anyone | Smart search; label searches use approved labels only | Built
Songs | POST/DELETE | /songs/:id/like | User | Like / unlike | Built
Songs | GET | /songs/:id/download-link, /songs/:id/download | User | Signed download, only if downloadable | Built
Catalogue | GET | /artists, /artists/:id/songs, /albums, /albums/:id/songs, /genres | Anyone | Browse | Built
Movies | GET | /movies, /movies/:id | Anyone | Published movie soundtracks | Built
Labels | GET | /moods | Anyone | Label list with counts of approved labels | Built
Playlists | GET/POST/PUT/DELETE | /playlists, /playlists/:id, /playlists/:id/songs | User | Manage playlists | Built
Me | GET | /users/me/recently-played, /users/me/liked-songs | User | Personal lists | Built
Discover | GET | /discover/search, /discover/youtube, /discover/trending?kind=&lang= | Anyone | Jamendo search, YouTube search, trending / popular videos | Built
Discover | POST | /discover/import | User | Copy a Creative Commons song into the library | Built
App | GET | /app/download | Anyone | Streams the latest APK | Built
Admin uploads | POST/GET | /admin/uploads, /admin/uploads/suggest-movie, job history | Admin | ZIP upload, name detection, progress | Built
Admin movies | GET/PATCH/POST | /admin/movies, /admin/movies/:id/songs, /publish, /order, /approve-labels, /classify | Admin | Review, publish, classify | Built
Admin songs | PATCH/POST | /admin/songs/:id, /suggest, /classification, /classify | Admin | Edit, approve or reject labels | Built
Admin albums | POST/PATCH | /admin/albums | Admin | Create / edit movies | Built
Admin labels | GET | /admin/labels | Admin | Label definitions | Built
Updater | GET | /app/version (mirror of version.json) | Anyone | Latest version for the in-app updater | Planned (phase 9)
Offline | GET | /songs/:id/download-link (already exists) | User | Used by the app's download manager | Planned (phase 7)
Admin analytics | GET | /admin/stats | Admin | Plays, top songs | Planned (future)

## Screens
Screen map - app vs website
☑ built, ☐ not built
Screen | Website | Android app | Admin panel | Notes
Login / register / Google | ☑ | ☑ (Google not yet) | ☑
Home (recent, popular, artists) | ☑ | ☑ | -
Trending + popular Telugu videos | ☑ | ☑ | - | YouTube embedded player
Search (library, Jamendo, YouTube) | ☑ | ☑ | -
Smart label search / label browser | ☑ | ☐ | - | Phase 5
Movie list and movie page | ☑ | ☐ | - | Phase 5
Now playing | ☑ | ☑ | -
Queue | ☐ | ☐ | - | Phase 6
Playlists and liked songs | ☑ | ☑ | -
Account / logout | ☑ | ☑ | -
Download app button | ☑ | - | -
Downloads (offline) | ☐ | ☐ | - | Phases 7-8
Update available prompt | - | ☐ | - | Phase 9
ZIP upload with movie-name detection | - | - | ☑
Movies list, review labels, publish | - | - | ☑ | Needs deployment (phase 10)

## Options
Choices and decisions
Option | What it gives | Effort | Catch | Recommendation
A. Android movies + labels screens | App matches the website | Medium | No new native code | Do next
B. Deploy admin to Cloudflare Pages | Upload from any device | Small | One setup step by you | Do soon
C. Private signing key | Safe updates for other users | Small | Needs keytool; one reinstall | Do before sharing widely
D. Offline downloads + offline mode | Listen without internet | Large | Native library; must test on a phone | After A
E. In-app updater | Update from inside the app | Medium | Android still shows its confirm prompt | After C
F. Player upgrades | Repeat, queue, recovery | Medium | - | Any time
G. Train a real classifier | Better label suggestions | Large | Needs licensed, labelled audio | Only if you have data
H. App locker (separate app) | Lock other apps with fingerprint + PIN | Large | Accessibility permission; phone-brand battery quirks | Your decision
Render paid plan / keep-alive | No sleeping server | Small | Paid, or pings | Optional

## Rules
Rules we keep
YouTube is played only in its own visible embedded player. No downloading, no audio extraction, no hidden player.
Songs can be downloaded only when the admin marks them downloadable and has the rights.
No music imported from sites without a licence.
Uploads need a rights confirmation and arrive as drafts; nothing is public until published.
Search uses only labels an admin has approved.
Secrets live in Render and GitHub settings only - never in the app, repo or chat.
The APK is built only when asked (tag vX.Y.Z or manual run). Takes about 18-25 minutes.